## BOM
Document No | Revision No | Effective Date | Created Date | Last Updated Date
IMS-F-25 | 4 | 2023-10-10 | 2025-11-10 15:07 | 2025-11-10 15:07
Project Code | Customer | Project Po No | Project Category | Project Quantity | Budget Material Cost | Actual Material Cost | Build By
P513 | Sophic | Sophic R&D OMR | Automated Intelligent Material Management System | 1 | 0 |  | Jim Chew,Wei Hoe,Jun Wei
Updated Date | Bom Line No | Status | Module | Description | Brand | Category | Part No | Unit Quantity | Total Quantity | Buyer Last Submitted Date | Rfq Updated Date | Rfq No | Pr Updated Date | Pr No | Unit Price | Total Price | Vendor Name | Vendor Quotation | Quotation Line No | Po No | Po Quantity | Estimate Delivery Date | Do No | Invoice No | Received Date | Received Quantity | Balance To Issue Out Quantity | Grn No
2026-01-12 13:54 | 31700 | PO Approved | ROTARY | A25.OMR.005.007 | Fabrication Part | Fabrication | A25.OMR.005.007 | 8 | 8 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 30 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 8 | 2026-01-20
2026-01-12 13:54 | 31701 | PO Approved | ROTARY | A25.OMR.005.008 | Fabrication Part | Fabrication | A25.OMR.005.008 | 8 | 8 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 30 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 8 | 2026-01-20
2026-01-12 13:54 | 31702 | PO Approved | ROTARY | A25.OMR.005.009 | Fabrication Part | Fabrication | A25.OMR.005.009 | 8 | 8 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 25 | 200 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 8 | 2026-01-20
2026-01-12 13:54 | 31703 | PO Approved | ROTARY | A25.OMR.006.004 | Fabrication Part | Fabrication | A25.OMR.006.004 | 1 | 1 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 230 | 230 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 1 | 2026-01-20
2026-01-12 13:54 | 31704 | PO Approved | ROTARY | A25.OMR.006.005 | Fabrication Part | Fabrication | A25.OMR.006.005 | 1 | 1 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 700 | 700 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 1 | 2026-01-20
2026-01-12 13:54 | 31705 | PO Approved | ROTARY | A25.OMR.006.006 | Fabrication Part | Fabrication | A25.OMR.006.006 | 4 | 4 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 400 | 1600 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 4 | 2026-01-20
2026-01-07 19:02 | 31706 | PO Approved | ROTARY | PS8080-8 Alu Profiles | Profile | Fabrication | A25.OMR.006.007 | 4 | 4 | 2026-01-07 15:10 | 2026-01-07 19:01 | RFQ4121341 | 2026-01-07 19:01 | PR5288391 | 34.7 | 138.8 | PBA LEADER MOTION SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/42541 | 1 | SAPO26010155 | 4 | 2026-01-10
2026-01-12 13:54 | 31707 | PO Approved | ROTARY | A25.OMR.006.008 | Fabrication Part | Fabrication | A25.OMR.006.008 | 4 | 4 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 60 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 4 | 2026-01-20
2026-01-14 17:05 | 31708 | PO Approved | ROTARY | A25.OMR.006.010 | Fabrication Part | Fabrication | A25.OMR.006.010 | 1 | 1 | 2026-01-14 11:28 | 2026-01-14 17:05 | RFQ4122531 | 2026-01-14 17:05 | PR5291531 | 450 | 450 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42926 | 1 | SAPO26010330 | 1 | 2026-01-27
2026-01-12 13:54 | 31709 | PO Approved | ROTARY | A25.OMR.006.013 | Fabrication Part | Fabrication | A25.OMR.006.013 | 4 | 4 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 55 | 220 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 4 | 2026-01-20
2026-01-12 13:54 | 31710 | PO Approved | ROTARY | A25.OMR.006.014 | Fabrication Part | Fabrication | A25.OMR.006.014 | 1 | 1 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 675 | 675 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 1 | 2026-01-20
2026-01-12 13:54 | 31711 | PO Approved | ROTARY | A25.OMR.006.016 | Fabrication Part | Fabrication | A25.OMR.006.016 | 4 | 4 | 2026-01-08 16:07 | 2026-01-12 13:53 | RFQ4116092 | 2026-01-12 13:54 | PR5290031 | 60 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42670 | 1 | SAPO26010117 | 4 | 2026-01-20
2026-01-14 17:13 | 31760 | PO Approved | GRIPPER | KC868-A16v3 ESP32-S3 16 channel GPIO module | KINCONY | Electrical | https://shop.kincony.com/products/kc868-a16v3-esp32-s3-16-channel-gpio-module?variant=44869042208933 | 1 | 1 | 2026-01-14 12:13 | 2026-01-14 17:13 | RFQ4116322 | 2026-01-14 17:13 | PR5291541 | 399 | 399 | JOMAN SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/42956 | #1 | SAPO26010223 | 1 | 2026-01-29
2025-12-13 00:22 | 31761 | PO Approved | GRIPPER | ESP32-S3-DEVKITC-1U-N8R8 |  | Electrical | https://www.digikey.my/en/products/detail/espressif-systems/ESP32-S3-DEVKITC-1U-N8R8/16162636?gclsrc=aw.ds&gad_source=1&gad_campaignid=17347342265&gbraid=0AAAAADrbLliu7s6qoBEFjB-FhVp2fmkZ8&gclid=CjwKCAiAzrbIBhA3EiwAUBaUdZMuhu15IIgzZJBF46KP_t8txk2zoyV4qk8i4K9EAJv7-IhTq1E10xoCc0kQAvD_BwE | 2 | 2 | 2025-12-13 00:20 | 2025-12-13 00:21 | RFQ4116381 | 2025-12-13 00:21 | PR5270921 | 13 | 109.2 | MOUSER ELECTRONIC - USD | https://internal.sophicauto.net/BOM/downloadFile/40183 https://internal.sophicauto.net/BOM/downloadFile/41099 | 1 | SAPO25120066 | 2 | 2025-12-19
2025-12-02 17:08 | 31762 | RFQ Sent | SOFTWARE | CODESYS Control Standard S (2302000050) | CODESYS | Software | https://store.codesys.com/en/codesys-control-standard-s-bundle.html | 1 | 1 |  | 2025-12-02 17:08 | RFQ4116312
2025-12-02 17:08 | 31763 | RFQ Sent | SOFTWARE | CODESYS SoftMotion Axes (8) (2305000010) | CODESYS | Software | https://store.codesys.com/en/codesys-softmotion-axes-8.html | 1 | 1 |  | 2025-12-02 17:08 | RFQ4116312
2025-12-15 11:40 | 31887 | PO Approved | LattePanda | M.2 E Key WiFi7 Bluetooth 5.4 Intel BE200 Wireless Network Card for LattePanda IOTA / Sigma | DFROBOT | Electrical | https://www.dfrobot.com/product-2877.html | 1 | 1 | 2025-12-10 17:15 | 2025-12-10 17:15 | RFQ4117032 | 2025-12-15 11:40 | PR5274241 | 218 | 218 | JOMAN SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/40826 | #1 | SAPO25120305 | 1 | 2025-12-23
2025-12-15 11:40 | 31888 | PO Approved | LattePanda | LattePanda IOTA Active Cooler (Aluminum Heatsink & Fan) | DFRobot | Electrical | https://www.dfrobot.com/product-2987.html | 1 | 1 | 2025-12-10 17:15 | 2025-12-10 17:15 | RFQ4117032 | 2025-12-15 11:40 | PR5274241 | 100 | 100 | JOMAN SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/40826 | #1 | SAPO25120305 | 1 | 2025-12-23
2026-01-07 14:48 | 32201 | PO Approved | LattePanda | Full-Function Evaluation Carrier Board for LattePanda Mu Compute Module | DFRobot | Electrical | https://www.dfrobot.com/product-2821.html | 1 | 1 | 2025-12-18 21:54 | 2025-12-18 21:54 | RFQ4118331 | 2026-01-07 14:47 | PR5288201 | 466 | 466 | JOMAN SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/41423 | #1 | SAPO26010110 | 1 | 2026-01-22
2026-01-07 14:48 | 32341 | PO Approved | HOIST Module | F1 20MM wide Elatech Italy Open-End Black PU/Polyurethane Steel Cord Flat Belt | Elatech | Mechanical | F1 20MM wide Elatech Italy Open-End Black PU/Polyurethane Steel Cord Flat Belt | 4 | 4 | 2025-12-16 18:25 | 2026-01-07 14:47 | RFQ4118341 | 2026-01-07 14:47 | PR5288211 | 400 | 1600 | LIM LEAN GIAP (BUTTERWORTH) SDN. BHD. | https://internal.sophicauto.net/BOM/downloadFile/41078 | 1 | SAPO26010112 | 4 | 2026-01-15
2026-01-07 14:48 | 32966 | PO Approved | USB to CAN adapter | CANable V2.0 Pro S | Makerbase | Electrical |  | 2 | 2 | 2026-01-02 13:08 | 2026-01-02 13:08 | RFQ4120291 | 2026-01-07 14:47 | PR5288201 | 98 | 196 | JOMAN SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/42045 | #1 | SAPO26010110 | 2 | 2026-01-22
2026-01-19 16:21 | 33413 | PO Approved | OMR-Mover | OMRG2-2101 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-19 09:18 | 2026-01-19 16:21 | RFQ4120941 | 2026-01-19 16:21 | PR5295531 | 620 | 1240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43263 | 1 | SAPO26010290 | 2 | 2026-01-24
2026-01-14 17:02 | 33414 | PO Approved | OMR-Mover | OMRG2-2102 | Fabrication Part | Fabrication |  | 10 | 10 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 38 | 380 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 10 | 2026-01-29
2026-01-14 17:02 | 33415 | PO Approved | OMR-Mover | OMRG2-2103 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 50 | 100 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33416 | PO Approved | OMR-Mover | OMRG2-2104 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 66 | 132 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33417 | PO Approved | OMR-Mover | OMRG2-2105 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 235 | 470 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33418 | PO Approved | OMR-Mover | OMRG2-2106 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 95 | 380 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 4 | 2026-01-29
2026-01-20 16:51 | 33419 | PO Approved | OMR-Mover | OMRG2-2107 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 195 | 390 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33420 | PO Approved | OMR-Mover | OMRG2-2108 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 15 | 30 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33421 | PO Approved | OMR-Mover | OMRG2-2109 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 15 | 60 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 4 | 2026-01-29
2026-01-15 10:21 | 33422 | PO Approved | OMR-Mover | OMRG2-2110 | Sheet Metal | Fabrication |  | 1 | 1 | 2026-01-15 10:16 | 2026-01-15 10:21 | RFQ4123861 | 2026-01-15 10:21 | PR5291591 | 120 | 120 | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43089 | 1 | SAPO26010243 | 1 | 2026-01-22
2026-01-14 17:15 | 33423 | PO Approved | OMR-Mover | OMRG2-2111 | Sheet Metal | Fabrication |  | 1 | 1 | 2026-01-14 17:06 | 2026-01-14 17:15 | RFQ4121092 | 2026-01-14 17:15 | PR5291571 | 95 | 95 | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43029 | 1 | SAPO26010224 | 1 | 2026-01-22
2026-01-14 17:15 | 33424 | PO Approved | OMR-Mover | OMRG2-2112 | Sheet Metal | Fabrication |  | 1 | 1 | 2026-01-14 17:06 | 2026-01-14 17:15 | RFQ4121092 | 2026-01-14 17:15 | PR5291571 | 28 | 28 | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43029 | 1 | SAPO26010224 | 1 | 2026-01-22
2026-01-15 16:43 | 33425 | PO Approved | OMR-Mover | OMRG2-2113 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-01-15 15:06 | 2026-01-15 16:43 | RFQ4123812 | 2026-01-15 16:43 | PR5292041 | 320 | 1280 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43108 | 1 | SAPO26010244 | 4 | 2026-01-16
2026-01-14 17:02 | 33453 | PO Approved | OMR-Mover | OMRG2-2202 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 120 | 120 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 1 | 2026-01-29
2026-01-14 17:02 | 33454 | PO Approved | OMR-Mover | OMRG2-2203- (1 pcs image , 1 pcs miroor) | Fabrication Part | Fabrication |  | 1 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 110 | 220 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-15 16:44 | 33455 | PO Approved | OMR-Mover | OMRG2-2204 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-15 10:37 | 2026-01-15 16:43 | RFQ4121071 | 2026-01-15 16:43 | PR5292051 | 55 | 110 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43090 | 1 | SAPO26010245 | 2 | 2026-01-20
2026-01-14 17:02 | 33456 | PO Approved | OMR-Mover | OMRG2-2205 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 20 | 40 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 2 | 2026-01-29
2026-01-14 17:02 | 33457 | PO Approved | OMR-Mover | OMRG2-2206 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 40 | 40 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 1 | 2026-01-29
2026-01-14 17:02 | 33458 | PO Approved | OMR-Mover | OMRG2-2207A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 100 | 100 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 1 | 2026-01-29
2026-01-14 17:02 | 33459 | PO Approved | OMR-Mover | OMRG2-2208 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 20 | 20 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 1 | 2026-01-29
2026-01-14 17:02 | 33460 | PO Approved | OMR-Mover | OMRG2-2201 | Fabrication Part | Fabrication | ? | 1 | 1 | 2026-01-14 14:43 | 2026-01-14 17:02 | RFQ4121082 | 2026-01-14 17:02 | PR5291521 | 780 | 780 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/42964 | 1 | SAPO26010222 | 1 | 2026-01-29
2026-01-07 15:11 | 33491 | RFQ Sent | ROTARY | A25.OMR.006.004.R1 | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-01-07 15:00 | RFQ4121351
2026-01-19 16:22 | 33535 | PO Approved | OMR-Mover | Urethane Molded Bearings | Misumi | Mechanical | UMRW45 | 10 | 10 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 32.45 | 324.5 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 10 | 2026-01-26
2026-01-19 16:22 | 33536 | PO Approved | OMR-Mover | Urethane Molded Bearings | Misumi | Mechanical | UMRHV45 | 4 | 4 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 64.35 | 257.4 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 4 | 2026-01-26
2026-01-19 16:22 | 33537 | PO Approved | OMR-Mover | MechaLock - Standard | Misumi | Mechanical | MLM12 | 4 | 4 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 157.14 | 628.56 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 4 | 2026-01-26
2026-01-19 16:22 | 33538 | PO Approved | OMR-Mover | Timing Pulleys T10 | Misumi | Mechanical | TTPA16T10200-A-N14 | 2 | 2 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 120.02 | 240.04 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 2 | 2026-01-26
2026-01-19 16:22 | 33539 | PO Approved | OMR-Mover | Timing Belts/T10 | Misumi | Mechanical | TTBU1150T10-200 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 179.43 | 179.43 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-01-19 16:22 | 33540 | PO Approved | OMR-Mover | Cam Followers Flat, Hex Socket | Misumi | Mechanical | C-CFFA18-40 | 2 | 2 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 43.83 | 87.66 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 2 | 2026-01-26
2026-01-19 16:22 | 33541 | PO Approved | OMR-Mover | Ball Bearings | Misumi | Mechanical | C-E6301ZZ | 4 | 4 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 4.15 | 16.6 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 4 | 2026-01-26
2026-01-19 16:22 | 33542 | PO Approved | OMR-Mover | Miniature Linear Guides | Misumi | Mechanical | SSEBN20G-100 | 4 | 4 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 291.83 | 1167.32 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 4 | 2026-01-26
2026-01-19 16:22 | 33543 | PO Approved | OMR-Mover | Slit Couplings Long, Clamping Type | Misumi | Mechanical | GSACL20-6-10 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 43.34 | 43.34 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-01-19 16:22 | 33544 | PO Approved | OMR-Mover | Timing Pulleys T5 | Misumi | Mechanical | E-TTPA40T5100-B-N10 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 61.14 | 61.14 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-01-19 16:22 | 33545 | PO Approved | OMR-Mover | Timing Belts/T5 | Misumi | Mechanical | TTBU550T5-100 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 46.07 | 46.07 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-01-19 16:22 | 33546 | PO Approved | OMR-Mover | Clamp Plates for Open End Belts T Type | Misumi | Mechanical | C-TBCR-T5100 | 2 | 2 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 11 | 22 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 2 | 2026-01-26
2026-01-19 16:22 | 33547 | PO Approved | OMR-Mover | Loosening Prevention Nuts for Bearing | Misumi | Mechanical | E-BNRS8 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 9.24 | 9.24 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-03-09 10:43 | 33548 | PO Approved | OMR-Mover | Flanged Small Ball Bearings Stainless Steel | Misumi [YHD] | Mechanical | C-SEFL608ZZ [BAL608ZZ-E-SUS] | 6 | 6 | 2026-03-05 15:53 | 2026-03-05 15:53 | RFQ4124221 | 2026-03-09 10:42 | PR5319311 | 1.06 | 25.2397 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45811 | 27 | SAPO26030261 | 6 | 2026-03-14
2026-01-19 16:22 | 33549 | PO Approved | OMR-Mover | Bearing Shaft Screws | Misumi | Mechanical | C-BMSB8-25 | 2 | 2 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 4.97 | 9.94 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 2 | 2026-01-26
2026-01-19 16:22 | 33550 | PO Approved | OMR-Mover | Bearing Shaft Screws | Misumi | Mechanical | C-BMSB8-15 | 1 | 1 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 4.6 | 4.6 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 1 | 2026-01-26
2026-01-19 16:22 | 33551 | PO Approved | OMR-Mover | Nylon Coated Cam Followers -Stainless Steel Body | Misumi | Mechanical | E-CFFRUCSS10-22 | 2 | 2 | 2026-01-17 13:55 | 2026-01-17 13:55 | RFQ4121442 | 2026-01-19 16:21 | PR5295701 | 134.96 | 269.92 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43176 | 1 | SAPO26010277 | 2 | 2026-01-26
2026-01-15 16:44 | 33552 | PO Approved | OMR-Mover | Slot Sensor | Panasonic | Mechanical | PM-F45 | 2 | 2 | 2026-01-15 10:10 | 2026-01-15 10:10 | RFQ4121452 | 2026-01-15 16:43 | PR5292031 | 25 | 50 | FLEXIBLE AUTOMATION SYSTEM SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43086 | 1 | SAPO26010246 | 2 | 2026-01-22
2026-01-15 16:44 | 33553 | PO Approved | OMR-Mover | Slot Sensor | Panasonic | Mechanical | PM-R45 | 1 | 1 | 2026-01-15 10:10 | 2026-01-15 10:10 | RFQ4121452 | 2026-01-15 16:43 | PR5292031 | 25 | 25 | FLEXIBLE AUTOMATION SYSTEM SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/43086 | 1 | SAPO26010246 | 1 | 2026-01-22
2026-02-09 12:17 | 34032 | PO Approved | OMR-Mover | OMRG2-2114 - Base Plate | Base Plate | Fabrication |  | 1 | 1 | 2026-02-09 09:51 | 2026-02-09 10:18 | RFQ4123851 | 2026-02-09 10:18 | PR5304651 | 920 | 920 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43109 | 1 | SAPO26020205 | 1 | 2026-02-25
2026-01-29 11:28 | 34406 | PO Approved | Telescopic | OMRG2-2301 | Fabrication Part | Fabrication |  | 1 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 450 | 900 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-01-29 11:28 | 34407 | PO Approved | Telescopic | OMRG2-2302 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 85 | 170 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-01-29 11:28 | 34408 | PO Approved | Telescopic | OMRG2-2303 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 40 | 80 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-01-29 11:28 | 34409 | PO Approved | Telescopic | OMRG2-2304 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 55 | 110 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-01-29 11:28 | 34410 | PO Approved | Telescopic | OMRG2-2305A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 40 | 160 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 4 | 2026-02-12
2026-01-29 11:28 | 34411 | PO Approved | Telescopic | OMRG2-2306 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 50 | 50 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 1 | 2026-02-12
2026-01-29 11:28 | 34412 | PO Approved | Telescopic | OMRG2-2307 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 30 | 30 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 1 | 2026-02-12
2026-01-29 11:28 | 34413 | PO Approved | Telescopic | OMRG2-2308 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 40 | 80 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-01-29 11:28 | 34414 | PO Approved | Telescopic | OMRG2-2310 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 70 | 70 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 1 | 2026-02-12
2026-01-29 11:28 | 34415 | PO Approved | Telescopic | OMRG2-2312 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-01-28 10:44 | 2026-01-29 11:27 | RFQ4125002 | 2026-01-29 11:28 | PR5300151 | 35 | 70 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/43835 | 1 | SAPO26010441 | 2 | 2026-02-12
2026-02-26 11:00 | 35688 | PO Approved | LATTEPANDA | DFROBOT ACTIVE COOLER, COMPUTE MODULE, ALUMINIUM - FIT0981 | DFROBOT | Electrical | https://my.element14.com/dfrobot/fit0981/active-cooler-compute-module-aluminium/dp/4457337?&CMP=KNC-GMY-GEN-SHOPPING-PERF-MAX-V1&mckv=_dc¦pcrid¦¦pkw¦¦pmt¦¦slid¦¦product¦4457337¦pgrid¦¦ptaid¦¦&gad_source=1&gad_campaignid=16896172745&gbraid=0AAAAAD8yeHkdfejnILuWhK9Oiy397xIFn&gclid=Cj0KCQiA7rDMBhCjARIsAGDBuECgEH9b8DvdzTzKvtwDKkoSx6XRP1tBEMRtxJzijrXgqctx7Y97hwYaAqQoEALw_wcB | 1 | 1 | 2026-02-20 10:55 | 2026-02-23 16:22 | RFQ4128811 | 2026-02-23 16:22 | PR5311781 | 51.34 | 51.34 | ELEMENT 14 SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45121 | 1 | SAPO26020422 | 1 | 2026-03-06
2026-02-13 16:00 | 35726 | PO Approved | OMR-MOVER | Parallel Keys | Misumi | Mechanical | KESH5-20 | 4 | 4 | 2026-02-12 23:18 | 2026-02-13 15:57 | RFQ4128872 | 2026-02-13 14:12 | PR5310271 | 9.79 | 39.16 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44873 | 3 | SAPO26020296 | 4 | 2026-02-22
2026-02-13 15:57 | 35727 | PO Approved | OMR-MOVER | Parallel Keys | Misumi | Mechanical | KES3-10 | 1 | 1 | 2026-02-12 23:18 | 2026-02-13 15:57 | RFQ4128872 | 2026-02-13 15:57 | PR5310321 | 11.33 | 11.33 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44873 | 3 | SAPO26020296 | 1 | 2026-02-22
2026-03-09 10:45 | 35728 | PO Approved | OMR-MOVER | Gear box | LIMING | Mechanical | ST-FO-75B19-5/7MP62A-70-A5 | 1 | 1 | 2026-03-06 01:57 | 2026-03-09 10:45 | RFQ4128991 | 2026-03-09 10:45 | PR5319361 | 2100 | 2100 | COPOLY TRADING SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45814 | 1 | SAPO26030245 | 1 | 2026-03-25
2026-02-13 15:59 | 35729 | PO Approved | OMR-MOVER | Heavy Load Low Profile Caster Swivel | Misumi | Mechanical | E-CLHS50-N | 4 | 4 | 2026-02-12 23:18 | 2026-02-13 15:57 | RFQ4128872 | 2026-02-13 15:59 | PR5310451 | 24.84 | 99.36 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44873 | 3 | SAPO26020295 | 4 | 2026-03-05
2026-02-13 15:59 | 35730 | PO Approved | TELESCOPIC | Jointed Timing Belt T5 | Misumi | Mechanical | E-LLTBJ-T5200-166 | 2 | 2 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 23.97 | 47.94 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 2 | 2026-03-05
2026-02-13 15:59 | 35731 | PO Approved | TELESCOPIC | Idlers T5 | Misumi | Mechanical | C-AHTFW20-T5200-8 | 4 | 4 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 62.66 | 250.64 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 4 | 2026-03-05
2026-02-13 15:59 | 35732 | PO Approved | TELESCOPIC | Pivot Pins Shouldered, Retaining Ring | Misumi | Mechanical | E-PHCCG8-46.5 | 4 | 4 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 46.38 | 185.52 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 4 | 2026-03-05
2026-02-13 15:59 | 35733 | PO Approved | TELESCOPIC | Linear Guides for for Heavy Load - Normal Clearance | Misumi | Mechanical | C-SX2RL24-440 | 6 | 6 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 309.14 | 1854.84 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 6 | 2026-03-05
2026-02-13 15:59 | 35734 | PO Approved | TELESCOPIC | Clamp Plates for Open End Belts T Type | Misumi | Mechanical | C-TBCR-T5200 | 4 | 4 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 12.4 | 49.6 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 4 | 2026-03-05
2026-02-13 15:59 | 35735 | PO Approved | TELESCOPIC | Clamp Plates for Open End Belts T Type | Misumi | Mechanical | C-TBCR-T10250 | 1 | 1 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 16.6 | 16.6 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 1 | 2026-03-05
2026-02-13 15:59 | 35736 | PO Approved | TELESCOPIC | Jointed Timing Belt T10 | Misumi | Mechanical | E-LLTBJ-T10250-100 | 1 | 1 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 32.03 | 32.03 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 1 | 2026-03-05
2026-02-13 15:59 | 35737 | PO Approved | TELESCOPIC | Idlers T10 | Misumi | Mechanical | C-AHTFW16-T10250-15 | 2 | 2 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 73.31 | 146.62 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 2 | 2026-03-05
2026-02-13 15:59 | 35738 | PO Approved | TELESCOPIC | Plastic Rollers | Misumi | Mechanical | RORPSS30-L25 | 2 | 2 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 56.66 | 113.32 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 2 | 2026-03-05
2026-02-13 15:59 | 35739 | PO Approved | TELESCOPIC | Timing Pulleys Aluminum/Steel T10 | Misumi | Mechanical | E-TTPA15T10250-B-N10 | 1 | 1 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 62.1 | 62.1 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 1 | 2026-03-05
2026-02-13 15:59 | 35740 | PO Approved | TELESCOPIC | Parallel Keys | Misumi | Mechanical | KES3-15 | 1 | 1 | 2026-02-12 23:13 | 2026-02-12 23:13 | RFQ4128902 | 2026-02-13 15:59 | PR5310451 | 11.33 | 11.33 | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/44872 | 1 | SAPO26020295 | 1 | 2026-03-05
2026-02-26 10:41 | 35741 | PO Approved | TELESCOPIC | Slot Sensor | Panasonic | Mechanical | PM-Y45 | 3 | 3 | 2026-02-20 10:37 | 2026-02-26 10:41 | RFQ4128981 | 2026-02-26 10:41 | PR5313341 | 25 | 75 | FLEXIBLE AUTOMATION SYSTEM SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45119 | 1 | SAPO26030014 | 3 | 2026-03-16
2026-02-26 16:06 | 35744 | RFQ Sent | ROTATE | OMRP513-F3001-00 | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-02-12 16:43 | RFQ4128922
2026-02-26 16:06 | 35745 | RFQ Sent | ROTATE | OMRP513-F3002-00 | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-02-12 16:43 | RFQ4128922
2026-02-26 16:06 | 35746 | RFQ Sent | ROTATE | OMRP513-F3003-00 | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-02-12 16:43 | RFQ4128922
2026-02-26 16:06 | 35747 | RFQ Sent | ROTATE | OMRP513-F3004-00 | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-02-12 16:43 | RFQ4128922
2026-02-26 16:06 | 35748 | RFQ Sent | ROTATE | OMRP513-F3005-00 | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-02-12 16:43 | RFQ4128922
2026-03-12 10:58 | 35800 | PO Approved | HOIST | OMRP513-F2001-00 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 70 | 280 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 4 | 2026-03-26
2026-03-12 10:58 | 35801 | PO Approved | HOIST | OMRP513-F2002-00 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 35 | 35 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 1 | 2026-03-26
2026-03-12 10:58 | 35802 | PO Approved | HOIST | OMRP513-F2003-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 85 | 170 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35803 | PO Approved | HOIST | OMRP513-F2004-00 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 275 | 275 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 1 | 2026-03-26
2026-03-12 10:58 | 35804 | PO Approved | HOIST | OMRP513-F2005-00 | Fabrication Part | Fabrication |  | 12 | 12 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 50 | 600 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 12 | 2026-03-26
2026-03-12 10:58 | 35805 | PO Approved | HOIST | OMRP513-F2006-00 | Fabrication Part | Fabrication |  | 6 | 6 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 25 | 150 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 6 | 2026-03-26
2026-03-12 10:58 | 35806 | PO Approved | HOIST | OMRP513-F2007-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 100 | 200 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35807 | PO Approved | HOIST | OMRP513-F2008-00 | Fabrication Part | Fabrication |  | 12 | 12 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 20 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 12 | 2026-03-26
2026-03-12 10:58 | 35808 | PO Approved | HOIST | OMRP513-F2009-00 | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 155 | 155 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 1 | 2026-03-26
2026-03-12 10:58 | 35809 | PO Approved | HOIST | OMRP513-F2010-00 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 135 | 540 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 4 | 2026-03-26
2026-03-12 10:58 | 35810 | PO Approved | HOIST | OMRP513-F2011-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 25 | 50 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35811 | PO Approved | HOIST | OMRP513-F2012-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 20 | 40 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35812 | PO Approved | HOIST | OMRP513-F2013-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 80 | 160 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35813 | PO Approved | HOIST | OMRP513-F2014-00 | Fabrication Part | Fabrication |  | 8 | 8 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 15 | 120 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 8 | 2026-03-26
2026-03-12 10:58 | 35814 | PO Approved | HOIST | OMRP513-F2015-00 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 18 | 72 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 4 | 2026-03-26
2026-03-12 10:58 | 35815 | PO Approved | HOIST | OMRP513-F2016-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 20 | 40 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35816 | PO Approved | HOIST | OMRP513-F2017-00 | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 20 | 40 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 2 | 2026-03-26
2026-03-12 10:58 | 35817 | PO Approved | HOIST | OMRP513-F2018-00 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 60 | 240 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 4 | 2026-03-26
2026-03-12 10:58 | 35818 | PO Approved | HOIST | OMRP513-F2019-00 | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 09:58 | 2026-03-12 10:55 | RFQ4129102 | 2026-03-12 10:57 | PR5322791 | 45 | 180 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45485 | 1 | SAPO26030317 | 4 | 2026-03-26
2026-03-11 20:11 | 35823 | PO Approved | Gripper | OMR513-F1001A | Fabrication Part | Fabrication |  | 6 | 6 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 25 | 150 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 6 | 2026-03-26
2026-03-11 20:11 | 35824 | PO Approved | Gripper | OMR513-F1002A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 70 | 140 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35825 | PO Approved | Gripper | OMR513-F1003A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 40 | 160 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 4 | 2026-03-26
2026-03-11 20:11 | 35826 | PO Approved | Gripper | OMR513-F1004A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 85 | 170 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35827 | PO Approved | Gripper | OMR513-F1005A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 120 | 480 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 4 | 2026-03-26
2026-03-11 20:11 | 35828 | PO Approved | Gripper | OMR513-F1006A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 40 | 160 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 4 | 2026-03-26
2026-03-11 20:11 | 35829 | PO Approved | Gripper | OMR513-F1007A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 100 | 400 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 4 | 2026-03-26
2026-03-11 20:11 | 35830 | PO Approved | Gripper | OMR513-F1008A | Fabrication Part | Fabrication |  | 4 | 4 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 80 | 320 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 4 | 2026-03-26
2026-03-11 20:11 | 35831 | PO Approved | Gripper | OMR513-F1009A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 25 | 50 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35832 | PO Approved | Gripper | OMR513-F1010A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 50 | 100 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35833 | PO Approved | Gripper | OMR513-F1011A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 40 | 80 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35834 | PO Approved | Gripper | OMR513-F1012A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 65 | 65 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-03-11 20:11 | 35835 | PO Approved | Gripper | OMR513-F1013A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 45 | 45 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-03-11 20:11 | 35836 | PO Approved | Gripper | OMR513-F1014A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 17 | 17 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-03-11 20:11 | 35837 | PO Approved | Gripper | OMR513-F1015A | Fabrication Part | Fabrication |  | 2 | 2 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 30 | 60 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 2 | 2026-03-26
2026-03-11 20:11 | 35838 | PO Approved | Gripper | OMR513-F1016A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 40 | 40 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-03-11 20:11 | 35839 | PO Approved | Gripper | OMR513-F1017A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 320 | 320 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-03-11 20:11 | 35840 | PO Approved | Gripper | OMR513-F1018A | Fabrication Part | Fabrication |  | 1 | 1 | 2026-03-02 17:35 | 2026-03-11 20:09 | RFQ4129132 | 2026-03-11 20:11 | PR5322431 | 18 | 18 | CLS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/45525 | 1 | SAPO26030313 | 1 | 2026-03-26
2026-02-23 15:31 | 35841 | RFQ Updated | Gripper | OMR513-S1000A | Sheet Metal | Fabrication |  | 4 | 4 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-02-23 15:31 | 35842 | RFQ Updated | Gripper | OMR513-S1001A | Sheet Metal | Fabrication |  | 1 | 1 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-02-23 15:31 | 35843 | RFQ Updated | Gripper | OMR513-S1002A | Sheet Metal | Fabrication |  | 2 | 2 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-02-23 15:31 | 35844 | RFQ Updated | Gripper | OMR513-S1003A | Sheet Metal | Fabrication |  | 1 | 1 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-02-23 15:31 | 35845 | RFQ Updated | Gripper | OMR513-S1004A | Sheet Metal | Fabrication |  | 1 | 1 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-02-23 15:31 | 35846 | RFQ Updated | Gripper | OMR513-S1005A | Sheet Metal | Fabrication |  | 1 | 1 | 2026-02-23 15:31 | 2026-02-23 15:31 | RFQ4129142 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45142 | 1
2026-03-05 15:46 | 35888 | RFQ Sent | HOIST | string wheel | MISUMI | Mechanical | HBGP40-21 | 6 | 6 |  | 2026-02-19 14:50 | RFQ4129242
2026-03-09 10:43 | 35889 | PO Approved | HOIST | bearing | MISUMI [YHD] | Mechanical | B6000ZZ [BAY6000ZZ] ] | 12 | 12 | 2026-03-05 15:51 | 2026-03-05 15:51 | RFQ4131262 | 2026-03-09 10:42 | PR5319311 | 0.52 | 24.7634 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45810 | 23 | SAPO26030261 | 12 | 2026-03-14
2026-03-09 10:43 | 35890 | PO Approved | HOIST | c clip | MISUMI [YHD] | Mechanical | STWS10 [TAS02-10] | 12 | 12 | 2026-03-05 15:51 | 2026-03-05 15:51 | RFQ4131262 | 2026-03-09 10:42 | PR5319311 | 0.58 | 27.6208 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45810 | 23 | SAPO26030261 | 12 | 2026-03-14
2026-03-05 15:46 | 35891 | RFQ Sent | HOIST | height sensor | height sensor | Mechanical | A0-139452_EP01 | 1 | 1 |  | 2026-02-19 14:50 | RFQ4129242
2026-03-05 15:46 | 35893 | RFQ Sent | HOIST | slipring | JINPAT | Mechanical | LPC-06A | 2 | 2 |  | 2026-02-19 14:50 | RFQ4129242
2026-03-05 15:44 | 35894 | RFQ Sent | ROTATE | slider bearing | MISUMI | Mechanical | C-SX2RL24-L_b | 4 | 4 |  | 2026-02-19 14:52 | RFQ4129252 |  |  |  |  | MISUMI MALAYSIA SDN BHD |  | 21
2026-03-05 15:44 | 35895 | RFQ Sent | ROTATE | clamp plate | MISUMI | Mechanical | C-TBCR-T5200 | 1 | 1 |  | 2026-02-19 14:52 | RFQ4129252 |  |  |  |  | MISUMI MALAYSIA SDN BHD |  | 21
2026-03-05 15:44 | 35896 | RFQ Sent | ROTATE | motor | PDV | Mechanical | PVD-PX110-100 | 1 | 1 |  | 2026-02-19 14:52 | RFQ4129252 |  |  |  |  | MISUMI MALAYSIA SDN BHD |  | 21
2026-03-09 10:43 | 35897 | PO Approved | GRIPPER | Pivot Pin | MISUMI [YHD] | Mechanical | SHCDG6-25 【Y-KCD32-D6-L25】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 4.18 | 66.3533 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35898 | PO Approved | GRIPPER | Pivot Pin | MISUMI [YHD] | Mechanical | SHCDG8-20 【Y-KCD32-D8-L20】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 5.1 | 80.9574 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35899 | PO Approved | GRIPPER | Bushing | MISUMI [YHD] | Mechanical | MDZB6-10 【OFV01-d6-L10】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 0.2 | 3.1748 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:46 | 35900 | PO Approved | GRIPPER | Photoelectric sensor | PANASONIC | Mechanical | pm-u25 | 6 | 6 | 2026-03-06 01:53 | 2026-03-06 01:53 | RFQ4130812 | 2026-03-09 10:44 | PR5319341 | 8.5 | 202.3935 | Fulitech Technology Co. Limited | https://internal.sophicauto.net/BOM/downloadFile/45744 | 1 | SAPO26030286 | 6 | 2026-03-18
2026-03-09 10:43 | 35901 | PO Approved | GRIPPER | Linear Guide | MISUMI [YHD] | Mechanical | SSEBWZ16G-110 【IAJ01-H16-L110】 | 2 | 2 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 35.63 | 282.7953 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 2 | 2026-03-14
2026-03-05 15:23 | 35902 | RFQ Reject | GRIPPER | Linear Guide Bearing | MISUMI | Mechanical | SSEBWZ16 | 2 | 2 |  | 2026-02-23 16:23 | RFQ4129671 |  |  |  |  | MISUMI MALAYSIA SDN BHD
2026-03-09 10:43 | 35903 | PO Approved | GRIPPER | Linear Shaft | MISUMI [YHD] | Mechanical | PSSFGZ6-50-M3-N3-SC15 【SCK14-D6-L50-M3-N3-S15】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 10.11 | 160.4861 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35904 | PO Approved | GRIPPER | Linear Bearing | MISUMI [YHD] | Mechanical | LMU6 【LMC02-d6】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 0.82 | 13.0167 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35905 | PO Approved | GRIPPER | Round Wire Coil Spring | MISUMI [YHD] | Mechanical | C-UL8-40 【E-YUL-D8-L40】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 0.15 | 2.3811 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35906 | PO Approved | GRIPPER | Bearing with Housing | MISUMI [YHD] | Mechanical | C-BGHA698ZZ-20 【E-BHJ21-698ZZ-h20】 | 1 | 1 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 3.65 | 14.485 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 1 | 2026-03-14
2026-03-09 10:43 | 35907 | PO Approved | GRIPPER | Pivot Pin | MISUMI [YHD] | Mechanical | SCLBRU5-12 【Y-KCD56-D5-L12】 | 2 | 2 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 6.75 | 53.5748 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:43 | 35908 | PO Approved | GRIPPER | Bushing | MISUMI [YHD] | Mechanical | MDZB5-5 【OFV01-d5-L5】 | 6 | 6 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 0.16 | 3.8098 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 6 | 2026-03-14
2026-03-09 10:43 | 35909 | PO Approved | GRIPPER | Bearing Spacer | MISUMI [YHD] | Mechanical | E-CLBUS5-8-7 【BKP11-d5-D8-L7】 | 2 | 2 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 3.48 | 27.6208 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:46 | 35910 | PO Approved | GRIPPER | Photoelectric sensor | PANASONIC | Mechanical | pm-l25 | 2 | 2 | 2026-03-06 01:53 | 2026-03-06 01:53 | RFQ4130812 | 2026-03-09 10:44 | PR5319341 | 8.5 | 67.4645 | Fulitech Technology Co. Limited | https://internal.sophicauto.net/BOM/downloadFile/45744 | 1 | SAPO26030286 | 2 | 2026-03-18
2026-03-09 10:43 | 35911 | PO Approved | GRIPPER | Retaining Rings C-Type | MISUMI [YHD] | Mechanical | STWS12 【TAS02-12】 | 8 | 8 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 0.63 | 20.0012 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 8 | 2026-03-14
2026-03-09 10:43 | 35912 | PO Approved | GRIPPER | Pivot Pin | MISUMI [YHD] | Mechanical | HCDG5-10 【MIC01-D5-L10】 | 2 | 2 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 1.75 | 13.8897 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 2 | 2026-03-14
2026-03-04 01:46 | 35913 | RFQ Sent | GRIPPER | Reflactor | BANNER | Mechanical | A0-158515 | 1 | 1 |  | 2026-03-04 01:46 | RFQ4130831
2026-03-09 10:43 | 35914 | PO Approved | GRIPPER | Bearing Spacer | MISUMI [YHD] | Mechanical | E-CLBUS12-15-1.5 【BKP11-d12-D15-L1.5】 | 4 | 4 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 3.7 | 58.7338 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 4 | 2026-03-14
2026-03-09 10:43 | 35915 | PO Approved | GRIPPER | Coupling | MISUMI [YHD] | Mechanical | GSACL20-5-6 【DEE13-D20-d5-e6】 | 1 | 1 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 5.86 | 23.2554 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 1 | 2026-03-14
2026-03-09 10:45 | 35916 | PO Approved | GRIPPER | Stepper Motor | Moons | Mechanical | AM17HD6426-BR01 | 1 | 1 | 2026-03-04 14:44 | 2026-03-09 10:45 | RFQ4130821 | 2026-03-09 10:45 | PR5319351 | 885 | 885 | VALUE SOURCES (M) SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45735 | 1 | SAPO26030285 | 1 | 2026-04-01
2026-03-11 15:04 | 36010 | PO Approved | OMR-Mover | OMRG2-2104- Repeat | Fabrication Part | Fabrication |  | 1 | 2 | 2026-03-11 14:57 | 2026-03-11 15:04 | RFQ4129661 | 2026-03-11 15:04 | PR5321001 | 66 | 132 | YS PRECISION ENGINEERING | https://internal.sophicauto.net/BOM/downloadFile/46314 | 1 | SAPO26030296 | 2 | 2026-03-13
2026-03-12 00:07 | 36279 | RFQ Approved | ROTARY | bearing | misumi [YHD] | Mechanical | HR30220J [HR30220J-NSK ] | 1 | 1 | 2026-03-12 00:07 | 2026-03-12 00:07 | RFQ4130402 |  |  |  |  | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/46459 | 9
2026-03-12 00:07 | 36280 | RFQ Approved | ROTARY | ball plungers | misumi [YHD] | Mechanical | FBPJS12 [ZAK52-M12 ] | 4 | 4 | 2026-03-12 00:07 | 2026-03-12 00:07 | RFQ4130402 |  |  |  |  | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/46459 | 9
2026-03-12 00:07 | 36281 | RFQ Approved | ROTARY | ball button | misumi [YHD] | Mechanical | TBBT12 [ ZAS81-M12] | 4 | 4 | 2026-03-12 00:07 | 2026-03-12 00:07 | RFQ4130402 |  |  |  |  | MISUMI MALAYSIA SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/46459 | 9
2026-03-12 00:07 | 36282 | RFQ Sent | ROTARY | bearing | unasis | Mechanical | IZ0100XV-RL | 1 | 1 |  | 2026-03-12 00:07 | RFQ4132491
2026-03-04 10:01 | 36360 | RFQ Sent | Safety Guide | OMR-STR-F1109A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:00 | 36361 | RFQ Sent | Safety Guide | OMR-STR-F1110A | Profile | Fabrication |  | 1 | 1 |  | 2026-03-04 09:54 | RFQ4130861
2026-03-04 10:01 | 36362 | RFQ Sent | Safety Guide | OMR-STR-F1111A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36363 | RFQ Sent | Safety Guide | OMR-STR-F1113A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36364 | RFQ Sent | Safety Guide | OMR-STR-F1114A | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36365 | RFQ Sent | Safety Guide | OMR-STR-F1115A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36366 | RFQ Sent | Safety Guide | OMR-STR-F1117A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36367 | RFQ Sent | Safety Guide | OMR-STR-F1118A | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36368 | RFQ Sent | Safety Guide | OMR-STR-F1119A | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-05 16:30 | 36369 | RFQ Sent | Safety Guide | OMR-STR-S1123A | Sheet Metal | Fabrication |  | 2 | 2 |  | 2026-03-04 09:55 | RFQ4130871 |  |  |  |  | JIAN WEI ADVANCED TECHNOLOGY SDN BHD | https://internal.sophicauto.net/BOM/downloadFile/45815 | 1
2026-03-04 10:01 | 36370 | RFQ Sent | Safety Guide | OMR-STR-F1124A | Fabrication Part | Fabrication |  | 1 | 1 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36371 | RFQ Sent | Safety Guide | OMR-STR-F1125A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-04 10:01 | 36372 | RFQ Sent | Safety Guide | OMR-STR-F1126A | Fabrication Part | Fabrication |  | 2 | 2 |  | 2026-03-04 09:54 | RFQ4130772
2026-03-09 10:43 | 36373 | PO Approved | Safety Guide | LM guide | Hiwin [YHD] | Mechanical | HGH25CA2R850Z0C [HGH25CA2R850Z0C] | 2 | 2 | 2026-03-05 18:18 | 2026-03-05 18:18 | RFQ4130782 | 2026-03-09 10:42 | PR5319311 | 88.87 | 705.3612 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45832 | 1 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:43 | 36374 | PO Approved | Safety Guide | Linear Bush Bearing | Misumi [YHD] | Mechanical | C-LHFCM20 [E-LME23-d20] | 2 | 2 | 2026-03-05 18:18 | 2026-03-05 18:18 | RFQ4130782 | 2026-03-09 10:42 | PR5319311 | 2.51 | 19.9219 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45832 | 1 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:43 | 36375 | PO Approved | Safety Guide | Shaft Holder | Misumi [YHD] | Mechanical | SKBHF20 [GFC01-D20] | 2 | 2 | 2026-03-05 18:18 | 2026-03-05 18:18 | RFQ4130782 | 2026-03-09 10:42 | PR5319311 | 5.72 | 45.3996 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45832 | 1 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:43 | 36376 | PO Approved | Safety Guide | Spring | Misumi [YHD] | Mechanical | WR27-100 [YWR-D27-L80] | 2 | 2 | 2026-03-05 18:18 | 2026-03-05 18:18 | RFQ4130782 | 2026-03-09 10:42 | PR5319311 | 0.9 | 7.1433 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45832 | 1 | SAPO26030261 | 2 | 2026-03-14
2026-03-09 10:43 | 36508 | PO Approved |  | SHIPPING |  | Mechanical |  |  | 1 | 2026-03-05 15:39 | 2026-03-05 15:39 | RFQ4129262 | 2026-03-09 10:42 | PR5319311 | 52.64 | 208.9018 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45808 | 10 | SAPO26030261 | 1 | 2026-03-14
2026-03-06 09:16 | 36516 | RFQ Sent | Safety Guide | OMR-STR-A1200A | Profile | Fabrication |  | 1 | 1 |  | 2026-03-05 18:10 | RFQ4131351
2026-03-09 10:43 | 36518 | PO Approved |  | SHIPPING |  | Mechanical |  |  | 1 | 2026-03-05 18:18 | 2026-03-05 18:18 | RFQ4130782 | 2026-03-09 10:42 | PR5319311 | 92.08 | 365.4195 | Dongguan YHD Supply Chain Management Co Ltd | https://internal.sophicauto.net/BOM/downloadFile/45832 | 1 | SAPO26030261 | 1 | 2026-03-14